## Goal 3 MCM Data
Strategic Goal | Measure | 2017-12-31 | 2018-03-31 | 2018-06-30 | 2018-09-30 | 2018-12-31 | 2019-03-31 | 2019-06-30 | 2019-09-30 | 2019-12-31 | 2020-03-31 | 2020-06-30 | 2020-09-30 | 2020-12-31 | 2021-03-31 | 2021-06-30 | 2021-09-30 | 2021-12-31 | 2022-03-31 | 2022-06-30 | 2022-09-30 | 2022-12-31 | 2023-03-31 | 2023-06-30 | 2023-09-30 | 2023-12-31 | 2024-03-31 | 2024-06-30 | 2024-09-30 | 2024-12-31 | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31
Goal 3 | Number of scientific manuscripts facilitating development of MCM published in the quarter | 8 | 8 | 12 | 12 | 9 | 7 | 8 | 13 | 8 | 7 | 7 | 8 | 6 | 11 | 12 | 11 | 19 | 12 | 13 | 13 | 14 | 17 | 11 | 7 | 8 | 9 | 5 | 5 | 4 | 11 | 12 | 7 | 3
Goal 3 | Number of external presentations facilitating development of MCM to Advisory Committees, Workshops, Professional Society meeetings, etc. presented in the quarter | 16 | 5 | 9 | 15 | 11 | 7 | 5 | 12 | 10 | 7 | 4 | 9 | 17 | 6 | 15 | 6 | 6 | 2 | 3 | 17 | 14 | 5 | 8 | 8 | 14 | 3 | 9 | 26 | 6 | 2 | 9 | 8 | 1

## Goal 3 IGT Testing
Milestone | # | Estimated Start Date | Actual Start Date | Estimated Completion Date | Actual Completion Date | Project Status
Reviewing final report on the collaborative study on the 1st international reference reagent for activated Factor XI; discussing the plans for the FXIa multi-assay performance study. | 1 | 2012-10-01 | 2012-10-01 | 2012-12-31 | 2012-12-31 | Completed
Waiting for NIBSC study protocol to review. | 2 | 2013-01-01 | 2013-01-01 | 2013-03-31 | 2013-03-31 | Completed
The international study for the first International Standard of Coagulation Factor XIa (manufactured by NIBSC) is planned for November 2013. | 3 | 2013-04-01 | 2013-04-01 | 2013-06-30 | 2013-06-30 | Completed
1. Reviewed the “Final report on the evaluation of the WHO Reference Reagent (RR) for Activated Blood Coagulation Factor XI (FXIa), Human” from the NIBSC which was presented to the Expert Committee on Biological Standardization (ECBS) in Geneva, October 21-25, 2013. 2. Reviewed ECBS 2013 document, “Proposal for the 1st WHO International Standard (IS) for Activated Coagulation Factor XI (FXIa)” also from the NIBSC. This IS will replace the Reference Reagent discussed above. OBRR decided to support the establishment of this new WHO standard. 3. A principal NIBSC scientist on the 1st IS FXIa standard study, Dr. Elaine Gray, will be visiting OBRR on November 6, 2013 to specifically discuss the design of the study. | 4 | 2013-07-01 | 2013-07-01 | 2013-09-30 | 2013-09-30 | Completed
CBER and the National Institute for Biological Standards and Control (NIBSC) (UK) are currently discussing design of the International Study CS504 to establish the 1st International Standard (IS) for Activated Coagulation Factor XI (FXIa), Human. The study is led by the NIBSC with the participation of CBER laboratory. The NIBSC study samples have been received by CBER laboratory on January 15, 2014. The primary goal of the collaborative study is to value assign the functional activity of the proposed 1st IS for FXIa, relative to the Reference Reagent for FXIa (NIBSC code 11/236). The secondary goal of the study is to explore the performance of the FXIa candidates and their use in the assessment of procoagulant activity by a variety of in-house and commercial methods used for release of Immune Globulin (IG), Intravenous or Subcutaneous products. The third goal of the collaborative study is specific to the CBER laboratory. We will evaluate the potency results, variability, and limits of detection of CBER’s investigational methods relative to other common tests and laboratories. | 5 | 2013-10-01 | 2013-10-01 | 2013-12-31 | 2013-12-31 | Completed
1. Completed participation in the NIBSC study to develop the 1st WHO IS for FXIa, NIBSC 13/100; a preliminary report was issued by the NIBSC on 4 April 2014 to the participants for review. 2. Data were presented at two regulatory meetings, the 5 February 2014 FDA-EMA-HC Blood Cluster meeting and 18 March 2014 teleconference with the EMA-EDQM Meeting on Establishment of Common Test for Procoagulant Activity of Immunoglobulins. CBER presented data on the commutability of the NIBSC FXIa standard between 9 methods used for procoagulant activity testing. 3. OBRR started preliminary non-binding discussions with the USP on a collaborative NIBSC-USP-FDA-industry multi-laboratory study on the harmonization of IG thrombogenicity testing. | 6 | 2014-01-01 | 2014-01-01 | 2014-03-30 | 2014-03-31 | Completed
Development of the immune globulin procoagulant activity methods and the WHO 1st International Standard for coagulation FXIa were discussed during the 18 June 2014 FDA/EMA/Health Canada (HC) Blood Cluster Teleconference. EMA laboratories will be invited to participate in the future multi-laboratory studies on the commutability of the WHO FXIa standard. | 7 | 2014-04-01 | 2014-04-01 | 2014-06-30 | 2014-06-30 | Completed
CBER reviewed the NIBSC report presented for ECBS approval entitled “WHO/BS/2014.2245 Value Assignment of the Candidate 1st International Standard for Activated Blood Coagulation Factor XI (FXIa), Human, NIBSC Code 13/100”. CBER supports the establishment of the 1st international standard for FXIa. However, we had critical comments regarding the commutability and labeling of this international standard which will be conveyed to the WHO at the ECBS meeting this month. | 8 | 2014-07-01 | 2014-07-01 | 2014-09-30 | 2014-09-30 | Completed
CBER continues collaboration with immune globulin manufacturers and international regulatory agencies on the laboratory methodologies that can detect and prevent distribution of potentially thrombogenic immune globulin products. Our efforts are presently focused on the harmonization of procoagulant activity measurements conducted by quality control laboratories. In November of 2014, CBER participated in the United States Pharmacopeia’s Expert Committee Meeting to discuss upcoming collaborative studies of inter- and intra-laboratory differences. A questionnaire was prepared to survey the current practices for procoagulant activity methods carried out for immunoglobulin products. The results of this survey will be used by the UK’s NIBSC to manufacture a panel of immune globulin samples with known procoagulant activity. CBER will participate in the evaluation of these samples as soon as they become available. | 9 | 2014-10-01 | 2014-10-01 | 2014-12-31 | 2014-12-31 | Completed
In March of 2015 CBER participated in several meetings with scientists from the European Medicines Agency, National Institute for Biological Standards and Control (NIBSC, United Kingdom) and the United States Pharmacopeia’s Expert Committee to discuss technical difficulties related to implementation of the 1st WHO International Standard for activated coagulation Factor XI (FXIa, NIBSC code 13/100). A consensus was reached that further research is needed to compare and harmonize different methods because the International Standard and multiple licensed immune globulin products have different compositions, and their effects on the assays may be different. Several international laboratory assay harmonization studies are now confirmed for 2015 and 2016. In preparation for these studies, CBER scientists are currently evaluating possible impacts of an assay reagent corn trypsin inhibitor and an immune globulin impurity apolipoprotein H on the candidate thrombogenicity assays. The results of CBER studies will support development of a standardized Immune Globulin Thrombogenicity Testing. | 10 | 2015-01-01 | 2015-01-01 | 2015-03-30 | 2015-03-31 | Completed
FDA participated in preparation of a draft proposal for the Joint USP-NIBSC-FDA project on Investigation on Assays for Procoagulant Activity of Immunoglobulin Products. The first draft of the project proposal was issued in April 2014. The collaborative project goals include the development of recommendations for refined and standardized testing procedures, validation of the testing recommendations, verification of procedures on a panel of immunoglobulin products, and will culminate in the publication of findings in a peer review journal. It is envisioned that the project will involve three multicenter collaborative laboratory studies. | 11 | 2015-04-01 | 2015-04-01 | 2015-06-30 | 2015-06-30 | Completed
Measurement of procoagulant activity in immune globulin products is still an unresolved issue recognized by FDA, product manufacturers and international regulatory agencies. FDA/CBER has been working with the European regulatory agencies to harmonize the two previously established initiatives, a US-led CBER/USP/NIBSC study and the European study sponsored by the Group 6B of the European Pharmacopoeia. In October of 2015, the parties agreed to establish a Global Working Group on Measurement of Procoagulant Activity in Immune Globulins with membership from each organization. The collaborative Working Group proposes to develop, refine and standardize testing procedures, evaluate optimized procedures in a small collaborative study, and verify these procedures on a panel of immune globulin products in a large collaborative study. The Working Group will work with the Expert Committee on Biological Standardization (ECBS) to inform the WHO on the need to establish new reference preparations such as the International Reference Panel for Procoagulant Immune Globulins. | 12 | 2015-07-01 | 2015-07-01 | 2015-09-30 | 2015-09-30 | Completed
FDA/CBER and the European regulatory agencies are working together on the establishment of a Global Working Group on Measurement of Procoagulant Activity in Immune Globulins. The collaborative Working Group is currently discussing a stake holder meeting with the Immune Globulin manufacturers and assay manufacturers to describe the state of the art in procoagulant activity testing. FDA is also working with the NIBSC, UK on the plans for collaborative studies and the utilization of the International Reference Panel for Procoagulant Immune Globulins. | 13 | 2015-10-01 | 2015-10-01 | 2015-12-31 | 2015-12-31 | Completed
The Global Working Group has agreed to hold a stakeholder meeting on the testing of pro-coagulant activity in immune globulins. Product and assay manufacturers, European regulatory agencies and the US FDA are now discussing agenda, time and place of the upcoming meeting. | 14 | 2016-01-01 | 2016-01-01 | 2016-03-30 | 2016-03-31 | Completed
No update to report this quarter | 15 | 2016-04-01 | 2016-04-01 | 2016-06-30 | 2016-06-30 | Completed
The Global Working Group on Immune Globulin Thrombogenicity Assays collaborated with the Plasma Protein Therapeutics Association (PPTA) to organize a stakeholder meeting on the testing of pro-coagulant activity in immune globulins in Washington, DC in September, 2016. During the meeting, Immune Globulin product manufacturers, IVD manufacturers, European regulatory agencies, USP and the US FDA agreed on the urgent need for collaborative studies to harmonize assay procedures. Scientists from the NIBSC, UK and the US FDA started working on the design of these harmonization studies. | 16 | 2016-07-01 | 2016-07-01 | 2016-09-30 | 2016-09-30 | Completed
No update to report this quarter | 17 | 2016-10-01 | 2016-10-01 | 2016-12-31 | 2016-12-31 | Completed
FDA is currently reviewing the summary for the Immunoglobulin Stakeholders Forum that was held September 7-8, 2016. The summary was prepared on behalf of the Global Working Group for the Measurement of Procoagulant Activity of Immunoglobulins. FDA is also working with the National Institute for Biological Standards and Control (NIBSC, United Kingdom) on the design of collaborative harmonization studies. | 18 | 2017-01-01 | 2017-01-01 | 2017-03-30 | 2017-03-31 | Completed
FDA participates in the Global Working Group for the Measurement of Procoagulant Activity of Immunoglobulins (IG) formed in collaboration with the European Directorate for the Quality of Medicines (EDQM), National Institute for Biological Standards and Control (NIBSC, UK), and United States Pharmacopeia (USP) to have industry-wide harmonized assays for detection of thrombogenic impurities and thus prevent distribution of unsafe IG products to patients. At the recommendation of the Immunoglobulin Stakeholders Forum that was held September 7-8, 2016, three smaller study groups (SG) were recently formed to address issues related to specific assays for procoagulant activity in IG products: (1) Thrombin Generation Tests (SG-TGT) chaired by Dr. Mikhail Ovanesov from CBER, FDA, (2) FXIa functional assays (SG-FXIa) chaired by Dr. Johannes Dodt from Paul-Ehrlich-Institut, Germany, and (3) Non-activated partial thromboplastin time assays (SG-NAPTT) chaired by Dr. Kevin Carrick from USP. The SG programs will include small collaborative laboratory investigations, and the results will be used to formulate harmonized assay protocols. The harmonized protocols will be verified further in a large multicenter study to be announced in 2018. | 19 | 2017-04-01 | 2017-04-01 | 2017-06-30 | 2017-06-30 | Completed
No update to report this quarter | 20 | 2017-07-01 | 2017-07-01 | 2017-09-30 | 2017-09-30 | Completed
No update to report this quarter | 21 | 2017-10-01 | 2017-10-01 | 2017-12-31 | 2017-12-31 | Completed
No update to report this quarter | 22 | 2018-01-01 | 2018-01-01 | 2018-03-30 | 2018-03-31 | Completed
US FDA participated in two meetings of the Global Working Group (GWG) on Immune Globulin Thrombogenicity Assays. FDA scientists were selected to chair a GWG’s study group on the harmonization of Thrombin Generation Tests, and are currently working with the National Institute of Biological Standards and Control (NIBSC), UK to design a collaborative study on Thrombin Generation Test procedures. The collaborative study will compare and harmonize commercial and in-house Thrombin Generation Tests using a specially prepared NIBSC reference panel comprised of representative licensed Immune Globulin products donated by the manufacturers. The participants in the upcoming Thrombin Generation study will represent the Immune Globulin stakeholders, including Immune Globulin product manufacturers, in vitro diagnostic product (IVD) manufacturers, international regulatory agencies, and the United States Pharmacopeia (USP). | 23 | 2018-04-01 | 2018-04-01 | 2018-06-30 | 2018-06-30 | Completed
No update to report this quarter | 24 | 2018-07-01 | 2018-07-01 | 2018-09-30 | 2018-09-30 | Completed
FDA, in collaboration with the NIBSC, UK, designed a collaborative study protocol for the Study Group for Thrombin Generation Tests (SG-TGT); a research collaboration between stakeholders in regulation, standardization, and manufacturing tasked with creating harmonized assay protocols for using TGT to assess FXIa procoagulant activity in IgG products. The primary goal of the SG-TGT collaborative study is to produce a harmonized TGT protocol specifically for FXIa activity testing in an IgG quality control laboratory. Participants will collaborate to determine best practices and reference materials for IgG testing. The SG-TGT study report will be aggregated into a harmonized protocol to be verified in a large multicenter study to be organized by the NIBSC in 2019. The harmonized TGT protocol is seeking to: 1. resolve technical issues produced by specific analytical variables; 2. unify assay performance and reduce center-to-center variability; 3. serve as templates for assay performance by participant agencies and manufacturers; 4. stimulate future collaborative studies among relevant stakeholders; and 5. facilitate an agreed upon specification that reflects the clinical safety of IgG products. The finalized protocol will be submitted to study participants in Spring of 2019 along with the samples prepared for this collaborative study. These samples were manufactured by the NIBSC team from the IgG materials and assay reagents sourced from the participating stakeholders. | 25 | 2018-10-01 | 2018-10-01 | 2018-12-31 | 2018-12-31 | Completed
No update to report this quarter | 26 | 2019-01-01 | 2019-01-01 | 2019-03-30 | 2019-03-31 | Completed
US FDA finalized the protocol for a collaborative study on Thrombin Generation Tests for Procoagulant Activity and worked with the NIBSC, UK on two preparation of two freeze-dried panels of immune globulin products, representing 12 immune globulin product formulations and 5 levels of procoagulant activity found in marketed products. This collaborative study, organized by the Global Working Group (GWG) on Immune Globulin Thrombogenicity Assays, will roll out in September 2019. The study is aimed to harmonize multiple thrombogenicity testing techniques used by Immune Globulin manufacturers and regulatory agencies. The study is supported by manufacturers of in vitro diagnostic assays who will evaluate optimal combinations of commercially available reagent kits, and immune globulin who will use their assay variants specifically optimized for their licensed immune globulin products. Results of the study will be analyzed by the FDA scientists in collaboration with all participants, and presented in a collaborative study report in early 2020. | 27 | 2019-04-01 | 2019-04-01 | 2019-06-30 | 2019-06-30 | Completed
An international collaborative laboratory study for the Study Group on Thrombin Generation Tests (SG-TGT) is underway. The results of this collaborative study, organized by the Global Working Group (GWG) on Immune Globulin Thrombogenicity Assays, will be available in early 2020. | 28 | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-09-30 | Completed
No update to report this quarter | 29 | 2019-10-01 | 2019-10-01 | 2019-12-31 | 2019-12-31 | Completed
An international collaborative laboratory exercise of the Study Group on Thrombin Generation Tests (SG-TGT) of the Global Working Group (GWG) on Immune Globulin Thrombogenicity Assays has been organized by the FDA/CBER in collaboration with the NIBSC, UK. One third of the participants, including the FDA laboratory, have completed the study and returned their data for analysis. The remaining participants expect completion of the study over the next several months. The FDA/CBER laboratory is now conducting preliminary review of the results and developing approaches for statistical analysis of data. The preliminary report of this collaborative study will be available in the third quarter of 2020. | 30 | 2020-01-01 | 2020-01-01 | 2020-03-30 | 2020-03-31 | Completed
An international collaborative laboratory exercise of the Study Group on Thrombin Generation Tests (SG-TGT) of the Global Working Group (GWG) on Immune Globulin Thrombogenicity Assays has been successfully completed by all study participants. Six laboratories provided the results and another three laboratories plan to submit the results in November, 2020. The FDA/CBER laboratory has developed the software for data analysis and is now conducting analysis of submitted data. | 31 | 2020-04-01 | 2020-04-01 | 2020-06-30 | 2020-06-30 | Completed
No additional update | 32 | 2020-07-01 | 2020-07-01 | 2020-09-30 | 2020-09-30 | Completed
No update to report this quarter | 33 | 2020-10-01 | 2020-10-01 | 2020-12-31 | 2020-12-31 | Completed
This report covers the progress on the international collaborative study on measurement of FXIa activity in immune globulin products by thrombin generation assay. The last dataset from the participating laboratories has been received in March of 2021, concluding the data collection stage of the study. CBER has finished the preliminary analysis of data from all participants and is currently conducting the statistical analysis for the final study report. The report completion is expected by September, 2021. | 34 | 2021-01-01 | 2021-01-01 | 2021-03-30 | 2021-03-31 | Completed
No update to report this quarter | 35 | 2021-04-01 | 2021-04-01 | 2021-06-30 | 2021-06-30 | Completed
FDA scientists finalized the analysis of the collaborative study on Thrombin Generation Tests for Procoagulant Activity and are now working with the NIBSC, UK on the final report this study. The collaborative study, organized by the Global Working Group (GWG) on Immune Globulin Thrombogenicity Assays, identified substantial differences in analytical performance of participating laboratories. The study results also suggested that harmonization of thrombogenicity testing can be achieved with a limited set of analytical recommendations which are compatible with the existing reagent and recording systems. | 36 | 2021-07-01 | 2021-07-01 | 2021-09-30 | 2021-09-30 | Completed
No update to report this quarter | 37 | 2021-10-01 | 2021-10-01 | 2021-12-31 | 2021-12-31 | Completed
CBER researchers finished analysis of data from the collaborative study to harmonize thrombin generation assays for measurement of procoagulant activity in immune globulins. The 10 study participants, which included immune globulin manufacturers, thrombin generation kit manufacturers and national regulatory bodies, provided data form 13 unique assays based on several commercial and in-house platforms. These assays were evaluated by a limit (cut off) test and a quantitative approach with Factor XIa and immune globulin calibration curves. Seven immune globulin samples representative of product excipients and formulations were tested under pre-defined assay conditions to find analytical prerequisites for robust and consistent assay performance over a wide range of procoagulant activities. All participants were able to discern between samples with low and high activity. Better agreement was observed between laboratories that had pre-optimized their assays for sensitivity to low procoagulant activities. The initial study results were presented at the European Pharmacopoeia Group of Experts 6B Blood Products meeting on March 17, 2022. The final report will be issued after consultations with study participants and co-organizers. | 38 | 2022-01-01 | 2022-01-01 | 2022-03-31 | 2022-03-31 | Completed
CBER researchers finished analysis of data from the collaborative study to harmonize thrombin generation assays for measurement of procoagulant activity in immune globulins. The 10 study participants, which included immune globulin manufacturers, thrombin generation kit manufacturers and national regulatory bodies, provided data form 13 unique assays based on several commercial and in-house platforms. These assays were evaluated by a limit (cut off) test and a quantitative approach with Factor XIa and immune globulin calibration curves. Seven immune globulin samples representative of product excipients and formulations were tested under pre-defined assay conditions to find analytical prerequisites for robust and consistent assay performance over a wide range of procoagulant activities. All participants were able to discern between samples with low and high activity. Better agreement was observed between laboratories that had pre-optimized their assays for sensitivity to low procoagulant activities. The initial study results were presented at the European Pharmacopoeia Group of Experts 6B Blood Products meeting on March 17, 2022. The final report will be issued after consultations with study participants and co-organizers. | 39 | 2022-04-01 | 2022-04-01 | 2022-06-30 | 2022-06-30 | Completed
FDA is conducting negotiations with the Global Working Group members on the design of future collaborative study to compare thrombin generation assay, chromogenic assay and NaPTT method. The new study will be partly based on results of thrombin generation collaborative study organized by CBER. | 40 | 2022-07-01 | 2022-07-01 | 2022-09-30 | 2022-09-30 | Completed
No update to report this quarter | 41 | 2022-10-01 | 2022-10-01 | 2022-12-31 | 2022-12-31 | Completed
FDA has prepared and distributed the report to participants for the international collaborative study to harmonize thrombin generation assays for measurement of procoagulant activity in immune globulins. The study report was shared with 10 different participants, including immune globulin manufacturers, thrombin generation kit manufacturers and national regulatory bodies. A total of 13 different methods were tested, including assays based on typical commercially available reagent and instrumentation kits. Participants tested 7 different immune globulin samples of varying procoagulant activity under a broad range of different assay conditions. These experiments were designed to evaluate assay conditions that can deliver robust assay performance and a consistent response to a wide range of procoagulant activity. Potency analysis for each sample was done centrally using assay parameters reported by participants. Most laboratories were able to discern between samples with low and high activity. Quantitative measurement of procoagulant activity was found to be sensitive to assay conditions, which were different between labs. Regardless of the source of reagents used, good agreement was observed between laboratories that had optimized their assays to be sensitive to a wide range activity in IG samples. The presented analysis of this study demonstrated principles for assay harmonization that can enable consistent measurement of procoagulant activity in immune globulins. The results of the study were presented for the #111 meeting of European Pharmacopoeia Group of Experts No. 6B (Human blood and blood products) on February 28, 2023. | 42 | 2023-01-01 | 2023-01-01 | 2023-03-31 | 2023-03-31 | Completed
FDA prepared “Participant response sheet” for participants of the international collaborative study to harmonize thrombin generation assays for measurement of procoagulant activity in immune globulins. The “Participant response sheet” was distributed among 9 participants to collect their feedback on the previously distributed study report. By June 30th, 2023, FDA received feedback from 5 participants. Overall, participants agree with the presentation of the study results and FDA recommendations. FDA addressed participants’ comments in the updated Study report. The one comment regarding rewording of FDA recommendations on thrombin generation assay will be addressed after further discussion. | 43 | 2023-04-01 | 2023-04-01 | 2023-06-30 | 2023-06-30 | Completed
No update to report this quarter | 44 | 2023-07-01 | 2023-07-01 | 2023-09-30 | 2023-09-30 | Completed
FDA recommendations for testing Immune Globulins for FXIa were rephrased to be direct and prescribing. | 45 | 2023-10-01 | 2023-10-01 | 2023-12-31 | 2023-12-31 | Completed
Figures and tables in the report were rearranged for convenience of the reader. Figures were enhanced to a level suitable for publication. | 46 | 2024-01-01 | 2024-01-01 | 2024-03-31 | 2024-03-31 | Completed
Some graphs were added to the report to improve clarity. Minor edits in the text were done. The report is under proof reading with the aim to finalize the report by the end of Q4, 2024. | 47 | 2024-04-01 | 2024-04-01 | 2024-06-30 | 2024-06-30 | Completed
Comments from co-authors were received. The comments are being addressed. An additional analysis is being performed to be included in the report. | 48 | 2024-07-01 | 2024-07-01 | 2024-09-30 | 2024-09-30 | Completed
The recommendations for FXIa assays (Thrombin Generation, Chromogenic assay, and NAPTT) were discussed within the working group. Additional statistical analysis is being added to the report. The draft editing is ongoing. | 49 | 2024-10-01 | 2024-10-01 | 2024-12-31 | 2024-12-31 | Completed | 45566 | 45566 | 45657 | 45657 | Completed