## Science Research Data Measures
Category | Measure Title | Measure Sub-Title | Measure | 2015-06-30 | 2015-07-31 | 2015-08-30 | 2015-09-30 | 2015-10-31 | 2015-11-30 | 2015-12-31 | 2016-01-31 | 2016-02-28 | 2016-03-31 | 2016-04-30 | 2016-05-31 | 2016-06-30 | 2016-07-31 | 2016-08-30 | 2016-09-30 | 2016-10-31 | 2016-11-30 | 2016-12-31 | 2017-01-31 | 2017-02-28 | 2017-03-31 | 2017-04-30 | 2017-05-31 | 2017-06-30 | 2017-07-31 | 2017-08-30 | 2017-09-30 | 2017-10-31 | 2017-11-30 | 2017-12-31 | 2018-01-31 | 2018-02-28 | 2018-03-31 | 2018-04-30 | 2018-05-31 | 2018-06-30 | 2018-07-31 | 2018-08-30 | 2018-09-30 | 2018-10-31 | 2018-11-30 | 2018-12-31 | 2019-01-31 | 2019-02-28 | 2019-03-31 | 2019-04-30 | 2019-05-31 | 2019-06-30 | 2019-07-31 | 2019-08-30 | 2019-09-30 | 2019-10-31 | 2019-11-30 | 2019-12-31 | 2020-01-31 | 2020-02-28 | 2020-03-31 | 2020-04-30 | 2020-05-31 | 2020-06-30 | 2020-07-31 | 2020-08-31 | 2020-09-30 | 2020-10-31 | 2020-11-30 | 2020-12-31 | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31 | 2027-04-30 | 2027-05-31 | 2027-06-30 | 2027-07-31 | 2027-08-31 | 2027-09-30 | 2027-10-31 | 2027-11-30 | 2027-12-31 | 2028-01-31 | 2028-02-29 | 2028-03-31 | 2028-04-30 | 2028-05-31 | 2028-06-30 | 2028-07-31 | 2028-08-31 | 2028-09-30 | 2028-10-31 | 2028-11-30 | 2028-12-31 | 2029-01-31 | 2029-02-28 | 2029-03-31 | 2029-04-30 | 2029-05-31 | 2029-06-30 | 2029-07-31 | 2029-08-31 | 2029-09-30 | 2029-10-31 | 2029-11-30 | 2029-12-31 | 2030-01-31 | 2030-02-28 | 2030-03-31 | 2030-04-30 | 2030-05-31 | 2030-06-30 | 2030-07-31 | 2030-08-31 | 2030-09-30
Science and Research | Product Applications | Regular SE Reports | Cumulative Number of Regular SE Reports received | [54 empty] | 3119 |  |  | 3211 |  |  | 4117 |  |  | 10463 |  |  | 10591 |  |  | 10682 |  |  | 10930 |  |  | 11148 | 11214 | 11366 | 11424 | 11472 | 11486 | 11513 | 11549 | 11579 | 11591 | 11764 | 11785 | 11886 | 11944 | 11948 | 11960 | 12019 | 12058 | 12058 | 12103 | 12110 | 12116 | 12125 | 12130 | 12130 | 12203 | 12204 | 12220
Science and Research | Product Applications | Regular SE Reports | Cumulative Number of Regular SE Reports closed | [54 empty] | 2966 |  |  | 3008 |  |  | 3111 |  |  | 3211 |  |  | 4669 |  |  | 5291 |  |  | 5418 |  |  | 5556 | 5558 | 5576 | 5620 | 5607 | 5618 | 5658 | 5721 | 5721 | 5721 | 5806 | 5820 | 5849 | 5872 | 5872 | 5882 | 5873 | 5891 | 5975 | 5975 | 5978 | 6007 | 6016 | 6020 | 6032 | 6049 | 6083 | 6123
Science and Research | Product Applications | Regular SE Reports | Total number of Regular SE Reports closed | [54 empty] | 52 |  |  | 42 |  |  | 103 |  |  | 100 |  |  | 1458 |  |  | 622 |  |  | 127 |  |  | 138 | 2 | 18 | 44 | -13 | 11 | 40 | 63 | 0 | 0 | 85 | 14 | 29 | 23 | 0 | 10 | 0 | 18 | 84 | 0 | 3 | 29 | 1 | 4 | 12 | 17 | 34 | 40
Science and Research | Product Applications | Provisional SE Reports | Cumulative Number of Provisional SE Reports received | [54 empty] | 3645 |  |  | 3645 |  |  | 3645 |  |  | 3645 |  |  | 3645 |  |  | 3645 |  |  | 3645 |  |  | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3646 | 3646 | 3646 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645 | 3645
Science and Research | Product Applications | Provisional SE Reports | Cumulative Number of Provisional SE Reports closed | [54 empty] | 3095 |  |  | 3119 |  |  | 3142 |  |  | 3142 |  |  | 3159 |  |  | 3161 |  |  | 3162 |  |  | 3162 | 3162 | 3162 | 3162 | 3192 | 3192 | 3192 | 3192 | 3192 | 3192 | 3223 | 3223 | 3223 | 3221 | 3221 | 3221 | 3216 | 3236 | 3246 | 3246 | 3246 | 3246 | 3246 | 3246 | 3246 | 3246 | 3246 | 3246
Science and Research | Product Applications | Exemption from SE submissions | Cumulative Number of Exemption from SE submissions received | [54 empty] | 701 |  |  | 755 |  |  | 891 |  |  | 1115 |  |  | 1469 |  |  | 2484 |  |  | 2789 |  |  | 3281 | 3307 | 3334 | 3353 | 3372 | 3502 | 3537 | 3567 | 3589 | 3656 | 3687 | 3775 | 3782 | 3940 | 4053 | 4086 | 4403 | 4408 | 4416 | 4455 | 4477 | 4481 | 4508 | 4652 | 4871 | 5018 | 5026 | 5032
Science and Research | Product Applications | Exemption from SE submissions | Cumulative Number of Exemption from SE submissions closed | [54 empty] | 584 |  |  | 680 |  |  | 745 |  |  | 798 |  |  | 983 |  |  | 1168 |  |  | 1508 |  |  | 1818 | 1818 | 2194 | 2251 | 2415 | 2415 | 2417 | 2417 | 2417 | 2417 | 2645 | 2658 | 2687 | 2764 | 2800 | 2800 | 2884 | 2887 | 3047 | 3160 | 3197 | 3312 | 3493 | 3612 | 3797 | 3797 | 3806 | 3807
Science and Research | Product Applications | Pre-Market Tobacco Applications (PMTAs) | Cumulative Number of PMTAs received | [54 empty] | 432 |  |  | 470 |  |  | 652 |  |  | 8011144 |  |  | 8017106 |  |  | 8038724 |  |  | 8039221 |  |  | 8080146 | 8085368 | 8085382 | 8085405 | 8093258 | 8093258 | 8093357 | 8098677 | 8311914 | 8311924 | 9049008 | 9049016 | 9049016 | 26359555 | 26359555 | 26359557 | 26479045 | 26479222 | 26479236 | 26604148 | 26604206 | 26604208 | 26604424 | 26604554 | 26604609 | 26606328 | 26606461 | 26606552
Science and Research | Product Applications | Pre-Market Tobacco Applications (PMTAs) | Cumulative Number of PMTAs closed | [54 empty] | 385 |  |  | 391 |  |  | 394 |  |  | 760 |  |  | 4459 |  |  | 58541 |  |  | 516988 |  |  | 7686278 | 7789749 | 7794209 | 7795697 | 7796450 | 7798020 | 7809999 | 7813937 | 7817226 | 7828779 | 7829621 | 8550893 | 8708913 | 8745280 | 8758435 | 8764608 | 8766503 | 25988657 | 26033675 | 26035134 | 26041096 | 26042528 | 26042441 | 26042464 | 26042715 | 26041837 | 26043430 | 26045440
Science and Research | Product Applications | Pre-Market Tobacco Applications (PMTAs) | Total number of PMTAs closed | [54 empty] | 2 |  |  | 6 |  |  | 3 |  |  | 366 |  |  | 3699 |  |  | 54082 |  |  | 458447 |  |  | 7169290 | 103471 | 4460 | 1488 | 753 | 1570 | 11979 | 3938 | 3289 | 11553 | 842 | 721272 | 158020 | 36367 | 13155 | 6173 | 1960 | 17222154 | 45018 | 1459 | 5962 | 1432 | 9 | 23 | 251 | 0 | 1593 | 2010
Science and Research | Product Applications | Modified Risk Tobacco Product Applications (MRTPAs) | Cumulative Number of MRTPAs received | 17 |  |  | 17 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 27 |  |  | 31 |  |  | 37 |  |  | 37 |  |  | 37 |  |  | 37 |  |  | 38 |  |  | 38 |  |  | 38 |  |  | 40 |  |  | 40 |  |  | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  |  | 42 |  |  | 47 |  |  | 47 |  |  | 48 |  |  | 51 |  |  | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 52 | 52 | 52 | 65 | 65 | 65 | 73 | 73 | 83
Science and Research | Product Applications | Modified Risk Tobacco Product Applications (MRTPAs) | Cumulative Number of MRTPAs closed | 7 |  |  | 7 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 9 |  |  | 17 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 19 |  |  | 21 |  |  | 21 |  |  | 21 |  |  | 29 |  |  | 29 |  |  | 29 |  |  | 33 |  |  | 33 |  |  | 33 |  |  | 38 |  |  | 38 | 38 | 38 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 47 | 47 | 41 | 47 | 47 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
Science and Research | Research Tracking System (RTS) | Developing a Science-Base for Tobacco Product Regulation: Research Projects | Number of active research projects across all funding mechanisms (reported on a biannual basis) | [61 empty] | 203 | 215 | 212 | 211 | 210 | 207 | 205 | 204 | 202 | 201 | 201 | 204 | 208 | 204 | 200 | 213 | 213 | 211 | 211 | 212 | 210 | 214 | 209 | 205 | 195 | 190 | 185 | 206 | 206 | 206 | 203 | 199 | 195 | 191 | 190 | 185 | 188 | 182 | 169 | 189 | 188 | 187

## Path Key Project
Category | Milestone | Project Description | # | Estimated Start Date | Actual Start Date | Estimated Completion Date | Actual Completion Date | Project Status
Science and Research | Develop draft survey instruments | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 1 | 2012-07-01 | 2012-07-01 | 2012-07-31 | 2012-07-01 | Completed
Science and Research | Prepare and submit Office of Management and Budget (OMB) package for field test and main study | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 2 | 2012-06-01 | 2012-06-01 | 2012-08-30 | 2012-08-01 | Completed
Science and Research | Obtain OMB Approval for Field Test | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 3 | 2012-10-01 | 2012-10-01 | 2012-11-30 | 2012-11-01 | Completed
Science and Research | Launch Field Test | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 4 | 2012-11-01 | 2012-11-01 | 2012-12-31 | 2012-12-05 | Completed
Science and Research | Complete Field Test analyses | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 5 | 2013-03-01 | 2013-03-01 | 2013-04-30 | 2013-04-01 | Completed
Science and Research | Submit OMB materials for main study | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 6 | 2013-06-01 | 2013-06-01 | 2013-07-31 | 2013-07-01 | Completed
Science and Research | Obtain OMB approval | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 7 | 2013-06-01 | 2013-06-01 | 2013-08-30 | 2013-08-23 | Completed
Science and Research | Launch baseline/Wave 1 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 8 | 2013-09-01 | 2013-09-01 | 2013-09-30 | 2013-09-12 | Completed
Science and Research | Complete Data Collection for baseline/Wave 1 | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 9 | 2014-11-01 | 2014-11-01 | 2014-12-31 | 2014-12-31 | Completed
Science and Research | Launch Wave 2 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 10 | 2014-11-01 | 2014-11-01 | 2014-10-31 | 2014-10-15 | Completed
Science and Research | Launch Wave 3 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 11 | 2015-10-01 | 2015-10-01 | 2015-10-31 | 2015-10-31 | Completed
Science and Research | Release Restricted Use Data File for baseline/Wave 1 Data to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 12 | 2015-11-01 | 2015-11-01 | 2015-12-31 | 2015-12-19 | Completed
Science and Research | New RFP Awarded to Contractor for PATH 2.0*** | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 13 | 2015-11-01 | 2015-11-01 | 2016-01-30 | 2016-01-14 | Completed
Science and Research | Release Public Use Data Set for baseline/Wave 1 Data | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 14 | 2016-06-01 | 2016-06-01 | 2016-08-30 | 2016-08-01 | Completed
Science and Research | Launch Wave 4 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 15 | 2016-10-01 | 2016-10-01 | 2016-12-31 | 2016-12-01 | Completed
Science and Research | Release Restricted Use Data Set from Wave 2 to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 16 | 2017-03-01 | 2017-03-01 | 2017-03-31 | 2017-03-15 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 1 Adult Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 17 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | Completed
Science and Research | Release Public Use Data Set from Wave 2 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 18 | 2017-10-01 | 2017-10-01 | 2017-06-30 | 2017-06-15 | Completed
Science and Research | Launch Special Collection - Youth Wave 4.5 | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 19 | 2017-10-01 | 2017-10-01 | 2017-12-31 | 2017-12-01 | Completed
Science and Research | Release Restricted Use Data Set from Wave 3 Data Collection to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 20 | 2018-03-01 | 2018-03-01 | 2018-05-30 | 2018-05-01 | Completed
Science and Research | Release Public Use Data Set from Wave 3 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 21 | 2018-09-01 | 2018-09-01 | 2018-09-30 | 2018-09-28 | Completed
Science and Research | Launch Wave 5 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 22 | 2018-10-01 | 2018-10-01 | 2018-12-31 | 2018-12-01 | Completed
Science and Research | Release Restricted Use Data Set from Wave 4 Data to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 23 | 2019-03-01 | 2019-03-01 | 2019-06-30 | 2019-05-30 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 2 Adult Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 24 | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-03-19 | Completed
Science and Research | Release Public Use Data Set from Wave 4 Data | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 25 | 2019-10-01 | 2019-10-01 | 2019-12-31 | 2019-11-30 | Completed
Science and Research | Complete Wave 5 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 26 | 2019-10-01 | 2019-10-01 | 2019-12-31 | 2019-11-30 | Completed
Science and Research | Launch W5.5 Special Data Collection - youth and young adults | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 27 | 2019-10-01 | 2019-10-01 | 2019-12-31 | 2019-12-01 | Completed
Science and Research | Release Restricted Use File from Wave 4.5 Youth Only Special Data Collection to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 28 | 2020-03-01 | 2020-03-01 | 2020-03-30 | 2020-03-19 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 3 Adult Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 29 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-03-05 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 4 Adult Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 30 | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 | Completed
Science and Research | Release Public Use File from Wave 4.5 Youth Only Special Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 31 | 2020-09-01 | 2020-09-01 | 2020-12-31 | 2020-09-16 | Completed
Science and Research | Launch Wave 6 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 32 | 2020-10-01 | 2020-10-01 | 2020-12-01 | 2021-03-01 | Completed
Science and Research | Release Restricted Use Data Set from Wave 5 Data to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 33 | 2021-02-01 | 2021-02-01 | 2021-03-01 | 2021-02-23 | Completed
Science and Research | Release Public Use Data Set from Wave 5 Data | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 34 | 2021-07-01 | 2021-07-01 | 2021-11-01 | 2021-09-29 | Completed
Science and Research | Complete W6 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 35 | 2021-10-01 | 2021-10-01 | 2021-11-30 | 2021-11-30 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 5 Adult Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 36 | 2021-12-16 | 2021-12-16 | 2021-12-16 | 2021-12-16 | Completed
Science and Research | Launch Wave 7 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the U | 37 | 2021-10-01 | 2021-10-01 | 2022-01-06 | 2022-01-06 | Completed
Science and Research | Release Restricted Use Data Set from Wave 5.5 Youth and Young Adults Special Data Collection to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 38 | 2022-04-01 | 2022-04-01 | 2022-04-26 | 2022-04-25 | Completed
Science and Research | Release Restricted Use Data Set from 2020 Adult Telephone Survey (Sept - Dec 2020) | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 39 | 2022-04-01 | 2022-04-01 | 2022-04-26 | 2022-04-25 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 5 Youth Collection - Part I | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 40 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | Completed
Science and Research | Release Biomarker Restricted Use Data Set from Wave 4 Youth Collection - Part I | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 41 | 2022-08-30 | 2022-12-16 | 2022-12-31 | 2022-12-16 | Completed
Science and Research | Release Public Use Data Set from Wave 5.5 Youth and Young Adults Special Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 42 | 2022-10-15 | 2022-10-07 | 2022-10-15 | 2022-10-07 | Completed
Science and Research | Release Public Use Data Set from 2020 Adult Telephone Survey (ATS) (Sep - Dec 2020) | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 43 | 2022-10-15 | 2022-10-07 | 2022-10-15 | 2022-10-07 | Completed
Science and Research | Complete Wave 7 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 44 | 2022-12-31 | 2023-04-02 | 2023-04-02 | 2023-04-30 | Completed
Science and Research | Launch Wave 7.5 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 45 | 2023-01-06 | 2023-04-03 | 2023-04-03 | 2023-04-30 | Completed
Science and Research | Release Restricted Use Data Set from Wave 6 Data Collection to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 46 | 2023-03-01 | 2023-03-31 | 2023-03-01 | 2023-03-31 | Completed
Science and Research | Release Public Use Data Set from Wave 6 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 47 | 2023-08-15 | 2023-09-18 | 2023-08-15 | 2023-09-18 | Completed
Science and Research | Complete Wave 7.5 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 48 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2023-12-31 | Completed
Science and Research | Launch Wave 8 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 49 | 2024-01-22 | 2024-01-22 | 2024-01-22 | 2024-01-22 | Completed
Science and Research | Release Restricted Use Data Set from Wave 7 Data Collection to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 50 | 2024-03-31 |  | 2024-03-31 |  | Not Yet Started
Science and Research | Release Public Use Data Set from Wave 7 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 51 | 2024-12-10 |  | 2024-12-10 |  | Not Yet Started
Science and Research | Complete Wave 8 Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 52 | 2024-12-31 |  | 2024-12-31 |  | Not Yet Started
Science and Research | Release Restricted Use File from Wave 7.5 Special Data Collection to Researchers | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 53 | 2025-03-31 |  | 2025-03-31 |  | Not Yet Started
Science and Research | Release Public Use File from Wave 7.5 Youth Only Special Data Collection | Implement the Population Assessment of Tobacco and Health (PATH) Study. The PATH Study is a nationally representative, longitudinal cohort study of approximately 46,000 non-users and users of tobacco products and those at risk for tobacco use across the United States. | 54 | 2025-06-30 |  | 2025-06-30 |  | Not Yet Started

## National Survey Key Project
Category | Project Title | Milestone | Project Description | # | Estimated Start Date | Actual Start Date | Estimated Completion Date | Actual Completion Date | Project Status
Science and Research | National Youth Tobacco Survey | Develop the 2016 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 1 | 2015-10-01 | 2015-10-01 | 2015-12-31 | 2015-11-30 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2016 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 2 | 2016-01-31 | 2016-01-31 | 2016-03-31 | 2016-02-01 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2016 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 3 | 2017-10-01 | 2017-10-01 | 2017-12-31 | 2017-12-01 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2017 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 4 | 2016-10-01 | 2016-10-01 | 2016-12-31 | 2016-11-01 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2017 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 5 | 2017-03-01 | 2017-03-01 | 2017-06-30 | 2017-05-30 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2017 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 6 | 2018-03-01 | 2018-03-01 | 2018-06-30 | 2018-06-14 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2018 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 7 | 2017-06-30 | 2017-06-30 | 2017-09-30 | 2017-07-01 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding the 2018 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 8 | 2018-03-01 | 2018-03-01 | 2018-06-30 | 2018-05-31 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2018 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 9 | 2019-03-01 | 2019-03-01 | 2019-06-30 | 2019-04-01 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2019 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 10 | 2018-03-01 | 2018-03-01 | 2018-06-30 | 2018-04-01 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2019 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 11 | 2019-03-01 | 2019-02-15 | 2019-06-30 | 2019-05-24 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2019 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 12 | 2019-03-01 | 2019-03-01 | 2019-12-31 | 2019-12-07 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2020 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 13 | 2019-03-01 | 2019-03-01 | 2019-07-31 | 2019-05-01 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2020 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 14 | 2020-03-01 | 2020-01-16 | 2020-04-30 | 2020-03-16 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2020 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 15 | 2020-10-01 | 2020-10-01 | 2020-12-31 | 2020-12-22 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2021 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 16 | 2019-06-01 | 2019-06-01 | 2020-11-30 | 2021-01-14 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2021 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 17 | 2021-03-01 | 2021-01-18 | 2021-05-31 | 2021-05-21 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2021 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 18 | 2021-10-01 | 2021-08-01 | 2022-04-15 | 2022-03-14 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2022 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 19 | 2021-03-01 | 2021-03-08 | 2021-11-30 | 2021-08-18 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2022 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 20 | 2022-01-17 | 2022-01-17 | 2022-05-31 | 2022-05-31 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2022 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 21 | 2022-10-01 | 2022-10-01 | 2023-04-15 | 2023-02-16 | Completed
Science and Research | National Youth Tobacco Survey | Develop the 2023 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 22 | 2022-03-01 | 2021-10-01 | 2022-11-30 | 2022-12-30 | Completed
Science and Research | National Youth Tobacco Survey | Start fielding 2023 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 23 | 2023-01-18 | 2023-03-09 | 2023-05-31 | 2023-06-16 | Completed
Science and Research | National Youth Tobacco Survey | Public use data set release (2023 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 24 | 2023-06-01 | 2023-06-17 | 2023-12-31 |  | Delayed
Science and Research | National Youth Tobacco Survey | Develop the 2024 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 25 | 2022-10-15 | 2022-10-15 | 2023-11-30 |  | Delayed
Science and Research | National Youth Tobacco Survey | Start fielding 2024 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 26 | 2024-01-15 | 2024-01-22 | 2024-05-31 |  | On Track
Science and Research | National Youth Tobacco Survey | Public use data set release (2024 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 27 | 2024-06-01 |  | 2024-11-30 |  | Not Yet Started
Science and Research | National Youth Tobacco Survey | Develop the 2025 survey instrument | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 28 | 2024-10-01 |  | 2024-12-31 |  | Not Yet Started
Science and Research | National Youth Tobacco Survey | Start fielding 2025 survey | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 29 | 2025-01-15 |  | 2025-05-31 |  | Not Yet Started
Science and Research | National Youth Tobacco Survey | Public use data set release (2025 data) | Implement the National Youth Tobacco Survey to monitor key tobacco-related indicators in a nationally representative sample of U.S. middle and high school students. | 30 | 2025-06-01 |  | 2025-11-30 |  | Not Yet Started
Formulas:
Actual Start Date = [Estimated Start Date]