## Measure Data
Title | Public Health Outcome | NCTR Strategic Goal | NCTR Strategic Objective | Abbreviated Measure | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
Outreach Measures | Maintain/enhance the collaborations (e.g., FDA Product Centers, government agencies, and industry) and increase outreach to advance communication of scientific knowledge | Promote Global Interactions in Regulatory Science | Promote global scientific interactions | Research Highlights Subscriptions |  |  | 57202 |  |  | 57521 |  |  | 57789 |  |  | 58866 |  |  | 58953 |  |  | 59260 |  |  | 59455 |  |  | N/A |  |  | N/A |  |  | N/A |  |  | 48399 |  |  | 48949 |  |  | 46210 |  |  | 50998 |  |  | 48343 |  |  | 48566 |  |  | 48807 |  |  | 48733 |  |  | 48964 |  |  | 47416 |  |  | 47490 |  |  | 47485 |  |  | 47727 |  |  | 47798 |  |  | 48525 |  |  | 48520 |  |  | 48610 |  |  | 49334 |  |  | 50556 |  |  | 52107 |  |  | 52709 |  |  | 54382 |  |  | 53782 |  |  | 55915 |  |  | 57834 |  |  | 59360 |  |  | 49942 |  |  | 51747 |  |  | 53910 |  |  | 56181 |  |  | 58587 | [14 empty] | 58385
Outreach Measures | Maintain/enhance the collaborations (e.g., FDA Product Centers, government agencies, and industry) and increase outreach to advance communication of scientific knowledge | Promote Global Interactions in Regulatory Science | Promote global scientific interactions | Science Insights Subscriptions |  |  | 45289 |  |  | 46086 |  |  | 47719 |  |  | 48979 |  |  | 49252 |  |  | 49671 |  |  | 50005 |  |  | N/A |  |  | N/A |  |  | N/A |  |  | 41543 |  |  | 42120 |  |  | 40101 |  |  | 43802 |  |  | 42360 |  |  | 42716 |  |  | 43111 |  |  | 43264 |  |  | 43615 |  |  | 42288 |  |  | 42465 |  |  | 42628 |  |  | 42914 |  |  | 43078 |  |  | 43894 |  |  | 43963 |  |  | 44181 |  |  | 44947 |  |  | 46156 |  |  | 47748 |  |  | 48396 |  |  | 50115 |  |  | 49611 |  |  | 51919 |  |  | 53749 |  |  | 55318 |  |  | 45868 |  |  | 48224 |  |  | 50360 |  |  | 52609 |  |  | 55002 | [14 empty] | 54889
Research Publication Measures | Increase the submission of manuscripts accepted for publication in scientific journals | Promote Global Interactions in Regulatory Science | Promote global scientific interactions | Manuscripts accepted | [41 empty] | 32 |  |  | 40 |  |  | 38 |  |  | 31 |  |  | 40 |  |  | 38 |  |  | 34 |  |  | 28 |  |  | 28 |  |  | 24 |  |  | 29 |  |  | 32 |  |  | 40 |  |  | 38 |  |  | 29 |  |  | 25 |  |  | 32 |  |  | 19 |  |  | 24 |  |  | 24 |  |  | 30 |  |  | 25 |  |  | 38 |  |  | 26 |  |  | 26 |  |  | 28 |  |  | 29 |  |  | 32 | [14 empty] | 23

## Key Project Data
NCTR Strategic Goal | NCTR Strategic Objective | Division or Office | Key Project Title | Key Project Objective | Key Project Description | Public Health Outcome | # | Milestone Description | Detailed Milestone Description | Estimated Milestone Start Date | Actual Milestone Start Date | Estimated Milestone Completion Date | Actual Milestone Completion Date | Milestone Status | Project Start | Project End
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 1 | Assess the effects of cannabinoids on human NSCs | Assess the effects of cannabinoids on human NSCs | 2022-04-01 | 2022-05-02 | 2022-06-30 | 2022-07-15 | Completed | 2022-04-01 | 2025-12-31
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 2 | Assess the effects of combinations of various cannabinoids on human NSCs | Assess the effects of combinations of various cannabinoids on human NSCs | 2022-07-01 | 2022-07-15 | 2022-09-30 | 2023-01-31 | Completed | 2022-04-01 | 2025-12-31
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 3 | Assess the effects of cannabinoids on human neural cells-differentiated from NSCs | Assess the effects of cannabinoids on human neural cells-differentiated from NSCs | 2022-10-01 | 2023-01-04 | 2023-06-30 | 2023-07-30 | Completed | 2022-04-01 | 2025-12-31
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 4 | Assess the effects of methadone and buprenorphine on human NSCs | Assess the effects of methadone and buprenorphine on human NSCs | 2023-07-01 | 2023-08-01 | 2024-02-28 | 2024-02-28 | Completed | 2022-04-01 | 2025-12-31
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 5 | Assess the effects of methadone and buprenorphine on human neural cells-differentiated from NSCs | Assess the effects of methadone and buprenorphine on human neural cells-differentiated from NSCs | 2023-07-01 | 2024-03-01 | 2024-10-31 | 2024-10-31 | Completed | 2022-04-01 | 2025-12-31
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 6 | Assess the effects of combination of methadone/buprenorphine and cannabinoids on human NSCs | Assess the effects of combination of methadone/buprenorphine and cannabinoids on human NSCs | 2024-01-01 | 2024-11-01 | 2025-02-28 | 2025-02-28 | Completed | 2022-04-01 | 2025-09-30
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 7 | Assess the effects of combination of methadone/buprenorphine and cannabinoids on human neural cells-differentiated from NSCs | Assess the effects of the combination of methadone/buprenorphine and cannabinoids on human neural cells-differentiated from NSCs | 2025-03-01 | 2025-06-05 | 2025-09-01 | 2025-09-01 | Completed | 2022-04-01 | 2025-09-30
Advance scientific approaches and tools required to support public health | Advance regulatory science through the development of new tools and approaches | N/A | Assessing the effects of methadone or buprenorphine and their combined use with cannabinoids on human neural stem cells. | The overall goal of this proposal is to assess the effects of methadone, buprenorphine, tetrahydrocannabinol (THC) and cannabidiol (CBD) and their combinations on the developing central nervous system (CNS), and to determine the toxic doses of each drug using human neural stem cell (NSC) models. | None | Although medication-assisted therapy (MAT) can significantly improve the overall condition of pregnant opioid users and their offspring, human studies have indicated MAT during pregnancy may adversely affect fetal brain development with the causal link between MAT and affected brain functions yet to be established. More evaluation is needed to clarify the effects of MAT on the developing brain and to determine whether different doses or durations of MAT have different effects. Using human NSC models, the dose-dependent and time-course exposure effects of methadone or buprenorphine on NSCs and neural cells will be determined. This information will support the Agency to guide the best and most appropriate use of methadone or buprenorphine by pregnant opioid users. | 8 | Prepare NCTR Final Report | Prepare NCTR Final Report and Close Study | 2025-09-01 | 2025-09-01 | 2026-01-30 | 2026-03-14 | Completed | 2022-04-01 | 2025-09-30